## Project_Plan_Gantt
2023-05-01 | [7 empty] | Holidays & Meetings:
WBS |  | Tasks | Owner | Plan Start | Days | Finish | FTEs | Hrs. | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24 | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18
1 | My Demo Project | [6 empty] | 984.8 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-05 | 2023-08-06 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-02 | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24
1.1 | Project planning & prep |  |  | 2023-05-12 | - | 2023-08-24 | - | bar: Hrs. 984.8; 2023-05-08 2023-05-12 to 2023-08-21 2023-08-24
1.1.1 |  | Supervison & coord | Liz | 2023-05-12 | 75 | 2023-08-24 | 0.4 | Hrs. 984.8: 240; 2023-05-08 2023-05-12: 1; 2023-05-08 2023-05-13: 1; 2023-05-08 2023-05-14: 1; 2023-05-15 2023-05-15: 1; 2023-05-15 2023-05-16: 1; 2023-05-15 2023-05-17: 1; 2023-05-15 2023-05-18: 1; 2023-05-15 2023-05-19: 1; 2023-05-15 2023-05-20: 1; 2023-05-15 2023-05-21: 1; 2023-05-22 2023-05-22: 1; 2023-05-22 2023-05-23: 1; 2023-05-22 2023-05-24: 1; 2023-05-22 2023-05-25: 1; 2023-05-22 2023-05-26: 1; 2023-05-22 2023-05-27: 1; 2023-05-22 2023-05-28: 1; 2023-05-29 2023-05-29: 1; 2023-05-29 2023-05-30: 1; 2023-05-29 2023-05-31: 1; 2023-05-29 2023-06-01: 1; 2023-05-29 2023-06-02: 1; 2023-05-29 2023-06-03: 1; 2023-05-29 2023-06-04: 1; 2023-06-05 2023-06-05: 1; 2023-06-05 2023-06-06: 1; 2023-06-05 2023-06-07: 1; 2023-06-05 2023-06-08: 1; 2023-06-05 2023-06-09: 1; 2023-06-05 2023-06-10: 1; 2023-06-05 2023-06-11: 1; 2023-06-12 2023-06-12: 1; 2023-06-12 2023-06-13: 1; 2023-06-12 2023-06-14: 1; 2023-06-12 2023-06-15: 1; 2023-06-12 2023-06-16: 1; 2023-06-12 2023-06-17: 1; 2023-06-12 2023-06-18: 1; 2023-06-19 2023-06-19: 1; 2023-06-19 2023-06-20: 1; 2023-06-19 2023-06-21: 1; 2023-06-19 2023-06-22: 1; 2023-06-19 2023-06-23: 1; 2023-06-19 2023-06-24: 1; 2023-06-19 2023-06-25: 1; 2023-06-26 2023-06-26: 1; 2023-06-26 2023-06-27: 1; 2023-06-26 2023-06-28: 1; 2023-06-26 2023-06-29: 1; 2023-06-26 2023-06-30: 1; 2023-06-26 2023-07-01: 1; 2023-06-26 2023-07-02: 1; 2023-07-03 2023-07-03: 1; 2023-07-03 2023-07-04: 1; 2023-07-03 2023-07-05: 1; 2023-07-03 2023-07-06: 1; 2023-07-03 2023-07-07: 1; 2023-07-03 2023-07-08: 1; 2023-07-03 2023-07-09: 1; 2023-07-10 2023-07-10: 1; 2023-07-10 2023-07-11: 1; 2023-07-10 2023-07-12: 1; 2023-07-10 2023-07-13: 1; 2023-07-10 2023-07-14: 1; 2023-07-10 2023-07-15: 1; 2023-07-10 2023-07-16: 1; 2023-07-17 2023-07-17: 1; 2023-07-17 2023-07-18: 1; 2023-07-17 2023-07-19: 1; 2023-07-17 2023-07-20: 1; 2023-07-17 2023-07-21: 1; 2023-07-17 2023-07-22: 1; 2023-07-17 2023-07-23: 1; 2023-07-24 2023-07-24: 1; 2023-07-24 2023-07-25: 1; 2023-07-24 2023-07-26: 1; 2023-07-24 2023-07-27: 1; 2023-07-24 2023-07-28: 1; 2023-07-24 2023-07-29: 1; 2023-07-24 2023-07-30: 1; 2023-07-31 2023-07-31: 1; 2023-07-31 2023-08-01: 1; 2023-07-31 2023-08-02: 1; 2023-07-31 2023-08-03: 1; 2023-07-31 2023-08-04: 1; 2023-07-31 2023-08-05: 1; 2023-07-31 2023-08-06: 1; 2023-08-07 2023-08-07: 1; 2023-08-07 2023-08-08: 1; 2023-08-07 2023-08-09: 1; 2023-08-07 2023-08-10: 1; 2023-08-07 2023-08-11: 1; 2023-08-07 2023-08-12: 1; 2023-08-07 2023-08-13: 1; 2023-08-14 2023-08-14: 1; 2023-08-14 2023-08-15: 1; 2023-08-14 2023-08-16: 1; 2023-08-14 2023-08-17: 1; 2023-08-14 2023-08-18: 1; 2023-08-14 2023-08-19: 1; 2023-08-14 2023-08-20: 1; 2023-08-21 2023-08-21: 1; 2023-08-21 2023-08-22: 1; 2023-08-21 2023-08-23: 1; 2023-08-21 2023-08-24: 1
1.1.2 |  | Develop plan | Liz | 2023-05-14 | 12 | 2023-05-30 | 0.3 | Hrs. 984.8: 28.8; 2023-05-08 2023-05-14: 1; 2023-05-15 2023-05-15: 1; 2023-05-15 2023-05-16: 1; 2023-05-15 2023-05-17: 1; 2023-05-15 2023-05-18: 1; 2023-05-15 2023-05-19: 1; 2023-05-15 2023-05-20: 1; 2023-05-15 2023-05-21: 1; 2023-05-22 2023-05-22: 1; 2023-05-22 2023-05-23: 1; 2023-05-22 2023-05-24: 1; 2023-05-22 2023-05-25: 1; 2023-05-22 2023-05-26: 1; 2023-05-22 2023-05-27: 1; 2023-05-22 2023-05-28: 1; 2023-05-29 2023-05-29: 1; 2023-05-29 2023-05-30: 1
1.1.3 |  | Develop budget | Bill | 2023-05-24 | 11 | 2023-06-07 | 0.2 | Hrs. 984.8: 17.6; 2023-05-22 2023-05-24: 1; 2023-05-22 2023-05-25: 1; 2023-05-22 2023-05-26: 1; 2023-05-22 2023-05-27: 1; 2023-05-22 2023-05-28: 1; 2023-05-29 2023-05-29: 1; 2023-05-29 2023-05-30: 1; 2023-05-29 2023-05-31: 1; 2023-05-29 2023-06-01: 1; 2023-05-29 2023-06-02: 1; 2023-05-29 2023-06-03: 1; 2023-05-29 2023-06-04: 1; 2023-06-05 2023-06-05: 1; 2023-06-05 2023-06-06: 1; 2023-06-05 2023-06-07: 1
1.1.4 |  | Schedule kickoff mtg. | Simon | 2023-05-17 | 1 | 2023-05-17 | 0.2 | Hrs. 984.8: 1.6; 2023-05-15 2023-05-17: 1
1.1.5 |  | Conduct kickoff mtg. | Jim | 2023-06-07 | 0 | 2023-06-06 | 8 | Hrs. 984.8: 0
1.2.1 | Conduct requirements analysis |  |  | 2023-05-24 | - | 2023-07-17 | - | bar: Hrs. 984.8; 2023-05-22 2023-05-24 to 2023-07-17 2023-07-17
|  | Develop interview forms | Bob | 2023-05-24 | 5 | 2023-05-30 | 2 | Hrs. 984.8: 80; 2023-05-22 2023-05-24: 1; 2023-05-22 2023-05-25: 1; 2023-05-22 2023-05-26: 1; 2023-05-22 2023-05-27: 1; 2023-05-22 2023-05-28: 1; 2023-05-29 2023-05-29: 1; 2023-05-29 2023-05-30: 1
|  | Conduct interviews | Gordon | 2023-05-30 | 3 | 2023-06-01 | 4 | Hrs. 984.8: 96; 2023-05-29 2023-05-30: 1; 2023-05-29 2023-05-31: 1; 2023-05-29 2023-06-01: 1
|  | Write prelim. requirements | Simon | 2023-06-30 | 5 | 2023-07-06 | 1 | Hrs. 984.8: 40; 2023-06-26 2023-06-30: 1; 2023-06-26 2023-07-01: 1; 2023-06-26 2023-07-02: 1; 2023-07-03 2023-07-03: 1; 2023-07-03 2023-07-04: 1; 2023-07-03 2023-07-05: 1; 2023-07-03 2023-07-06: 1
|  | Conduct walk-thru | Jim | 2023-07-06 | 2 | 2023-07-07 | 8 | Hrs. 984.8: 128; 2023-07-03 2023-07-06: 1; 2023-07-03 2023-07-07: 1
|  | Update requirements doc. | Jim | 2023-07-08 | 6 | 2023-07-17 | 2 | Hrs. 984.8: 96; 2023-07-03 2023-07-08: 1; 2023-07-03 2023-07-09: 1; 2023-07-10 2023-07-10: 1; 2023-07-10 2023-07-11: 1; 2023-07-10 2023-07-12: 1; 2023-07-10 2023-07-13: 1; 2023-07-10 2023-07-14: 1; 2023-07-10 2023-07-15: 1; 2023-07-10 2023-07-16: 1; 2023-07-17 2023-07-17: 1
1.2.2 | Establish requirements baseline |  |  | 2023-07-15 | - | 2023-08-03 | - | bar: Hrs. 984.8; 2023-07-10 2023-07-15 to 2023-07-31 2023-08-03
|  | Publish draft req. doc. | Simon | 2023-07-15 | 1 | 2023-07-17 | 1 | Hrs. 984.8: 8; 2023-07-10 2023-07-15: 1; 2023-07-10 2023-07-16: 1; 2023-07-17 2023-07-17: 1
|  | Conduct req. review mtg. | Gordon | 2023-07-19 | 2 | 2023-07-20 | 8 | Hrs. 984.8: 128; 2023-07-17 2023-07-19: 1; 2023-07-17 2023-07-20: 1
|  | Incorporate comments | Dave | 2023-07-26 | 5 | 2023-08-01 | 2 | Hrs. 984.8: 80; 2023-07-24 2023-07-26: 1; 2023-07-24 2023-07-27: 1; 2023-07-24 2023-07-28: 1; 2023-07-24 2023-07-29: 1; 2023-07-24 2023-07-30: 1; 2023-07-31 2023-07-31: 1; 2023-07-31 2023-08-01: 1
|  | Send document for signatures | Gordon | 2023-08-02 | 2 | 2023-08-03 | 1 | Hrs. 984.8: 16; 2023-07-31 2023-08-02: 1; 2023-07-31 2023-08-03: 1
|  | Establish formal baseline | Mel | 2023-08-03 | 1 | 2023-08-03 | 0.1 | Hrs. 984.8: 0.8; 2023-07-31 2023-08-03: 1
| Next Major WBS Element |  |  | 2023-06-16 | - | 2023-06-30 | - | bar: Hrs. 984.8; 2023-06-12 2023-06-16 to 2023-06-26 2023-06-30
|  | Task |  | 2023-06-16 | 3 | 2023-06-20 | 1 | Hrs. 984.8: 24; 2023-06-12 2023-06-16: 1; 2023-06-12 2023-06-17: 1; 2023-06-12 2023-06-18: 1; 2023-06-19 2023-06-19: 1; 2023-06-19 2023-06-20: 1
|  | Task |  | 2023-06-20 | 3 | 2023-06-22 | 0 | Hrs. 984.8: 0; 2023-06-19 2023-06-20: 1; 2023-06-19 2023-06-21: 1; 2023-06-19 2023-06-22: 1
|  | Task |  | 2023-06-22 | 3 | 2023-06-26 | 0 | Hrs. 984.8: 0; 2023-06-19 2023-06-22: 1; 2023-06-19 2023-06-23: 1; 2023-06-19 2023-06-24: 1; 2023-06-19 2023-06-25: 1; 2023-06-26 2023-06-26: 1
|  | Task |  | 2023-06-26 | 3 | 2023-06-28 | 0 | Hrs. 984.8: 0; 2023-06-26 2023-06-26: 1; 2023-06-26 2023-06-27: 1; 2023-06-26 2023-06-28: 1
|  | Task |  | 2023-06-28 | 3 | 2023-06-30 | 0 | Hrs. 984.8: 0; 2023-06-26 2023-06-28: 1; 2023-06-26 2023-06-29: 1; 2023-06-26 2023-06-30: 1
| Next Major WBS Element |  |  | 2023-06-30 | - | 2023-07-28 | - | bar: Hrs. 984.8; 2023-06-26 2023-06-30 to 2023-07-24 2023-07-28
|  | Task |  | 2023-06-30 | 5 | 2023-07-06 | 0 | Hrs. 984.8: 0; 2023-06-26 2023-06-30: 1; 2023-06-26 2023-07-01: 1; 2023-06-26 2023-07-02: 1; 2023-07-03 2023-07-03: 1; 2023-07-03 2023-07-04: 1; 2023-07-03 2023-07-05: 1; 2023-07-03 2023-07-06: 1
|  | Task |  | 2023-07-06 | 5 | 2023-07-12 | 0 | Hrs. 984.8: 0; 2023-07-03 2023-07-06: 1; 2023-07-03 2023-07-07: 1; 2023-07-03 2023-07-08: 1; 2023-07-03 2023-07-09: 1; 2023-07-10 2023-07-10: 1; 2023-07-10 2023-07-11: 1; 2023-07-10 2023-07-12: 1
|  | Task |  | 2023-07-12 | 5 | 2023-07-18 | 0 | Hrs. 984.8: 0; 2023-07-10 2023-07-12: 1; 2023-07-10 2023-07-13: 1; 2023-07-10 2023-07-14: 1; 2023-07-10 2023-07-15: 1; 2023-07-10 2023-07-16: 1; 2023-07-17 2023-07-17: 1; 2023-07-17 2023-07-18: 1
|  | Task |  | 2023-07-18 | 5 | 2023-07-24 | 0 | Hrs. 984.8: 0; 2023-07-17 2023-07-18: 1; 2023-07-17 2023-07-19: 1; 2023-07-17 2023-07-20: 1; 2023-07-17 2023-07-21: 1; 2023-07-17 2023-07-22: 1; 2023-07-17 2023-07-23: 1; 2023-07-24 2023-07-24: 1
|  | Task |  | 2023-07-24 | 5 | 2023-07-28 | 0 | Hrs. 984.8: 0; 2023-07-24 2023-07-24: 1; 2023-07-24 2023-07-25: 1; 2023-07-24 2023-07-26: 1; 2023-07-24 2023-07-27: 1; 2023-07-24 2023-07-28: 1
| Next Major WBS Element |  |  | 2023-07-29 | - | 2023-08-07 | - | bar: Hrs. 984.8; 2023-07-24 2023-07-29 to 2023-08-07 2023-08-07
|  | Task |  | 2023-07-29 | 2 | 2023-08-01 | 0 | Hrs. 984.8: 0; 2023-07-24 2023-07-29: 1; 2023-07-24 2023-07-30: 1; 2023-07-31 2023-07-31: 1; 2023-07-31 2023-08-01: 1
|  | Task |  | 2023-08-01 | 2 | 2023-08-02 | 0 | Hrs. 984.8: 0; 2023-07-31 2023-08-01: 1; 2023-07-31 2023-08-02: 1
|  | Task |  | 2023-08-02 | 2 | 2023-08-03 | 0 | Hrs. 984.8: 0; 2023-07-31 2023-08-02: 1; 2023-07-31 2023-08-03: 1
|  | Task |  | 2023-08-03 | 2 | 2023-08-04 | 0 | Hrs. 984.8: 0; 2023-07-31 2023-08-03: 1; 2023-07-31 2023-08-04: 1
|  | Task |  | 2023-08-04 | 2 | 2023-08-07 | 0 | Hrs. 984.8: 0; 2023-07-31 2023-08-04: 1; 2023-07-31 2023-08-05: 1; 2023-07-31 2023-08-06: 1; 2023-08-07 2023-08-07: 1
| Next Major WBS Element |  |  | 2023-08-05 | - | 2023-09-04 | - | bar: Hrs. 984.8; 2023-07-31 2023-08-05 to 2023-09-04 2023-09-04
|  | Task |  | 2023-08-05 | 5 | 2023-08-11 | 0 | Hrs. 984.8: 0; 2023-07-31 2023-08-05: 1; 2023-07-31 2023-08-06: 1; 2023-08-07 2023-08-07: 1; 2023-08-07 2023-08-08: 1; 2023-08-07 2023-08-09: 1; 2023-08-07 2023-08-10: 1; 2023-08-07 2023-08-11: 1
|  | Task |  | 2023-08-11 | 5 | 2023-08-17 | 0 | Hrs. 984.8: 0; 2023-08-07 2023-08-11: 1; 2023-08-07 2023-08-12: 1; 2023-08-07 2023-08-13: 1; 2023-08-14 2023-08-14: 1; 2023-08-14 2023-08-15: 1; 2023-08-14 2023-08-16: 1; 2023-08-14 2023-08-17: 1
|  | Task |  | 2023-08-17 | 5 | 2023-08-23 | 0 | Hrs. 984.8: 0; 2023-08-14 2023-08-17: 1; 2023-08-14 2023-08-18: 1; 2023-08-14 2023-08-19: 1; 2023-08-14 2023-08-20: 1; 2023-08-21 2023-08-21: 1; 2023-08-21 2023-08-22: 1; 2023-08-21 2023-08-23: 1
|  | Task |  | 2023-08-23 | 5 | 2023-08-29 | 0 | Hrs. 984.8: 0; 2023-08-21 2023-08-23: 1; 2023-08-21 2023-08-24: 1; 2023-08-21 2023-08-25: 1; 2023-08-21 2023-08-26: 1; 2023-08-21 2023-08-27: 1; 2023-08-28 2023-08-28: 1; 2023-08-28 2023-08-29: 1
|  | Task |  | 2023-08-29 | 5 | 2023-09-04 | 0 | Hrs. 984.8: 0; 2023-08-28 2023-08-29: 1; 2023-08-28 2023-08-30: 1; 2023-08-28 2023-08-31: 1; 2023-08-28 2023-09-01: 1; 2023-08-28 2023-09-02: 1; 2023-08-28 2023-09-03: 1; 2023-09-04 2023-09-04: 1
Note: Calendar week dates begin on Mondays.
The formulaes in colum E are used to link the tasks so they automatically start after a pre-requisite task. You can replace these with a hard coded date to FIX the dates for any task.

## Holidays
Holidays for All Staff
2008-05-26
2008-07-04
2008-09-01
2008-10-13
The Gantt chart will skip over these dates when calculating end_dates.
If you add extra holidays - redefine the "Holidays" named range
under: Insert-Name-Define

## ReadMe_Notes
Installation: | Requires the Analysis ToolPak Add-in to be turned on (under Tools-Add Ins)
Make sure the bank holiday sheet has the correct dates for your country.
Using: | Tasks, start dates and durations can be entered into the white cells.
The grey cells will calculate automatically.
The summary tasks (shown in Blue) use functions to add up the duration of the sub-tasks below.
To link tasks together so they run consecutively, you can use simple formulas in column E to set the start_date of one task = end_date of the previous task.
For tasks that have a fixed start date just type in the date required.
The calculated end dates in column G assume that no-one will work weekends or bank holidays.
You can also add formatting to row 1 to indicate bank holidays and key project meetings or milestones.
The hours calculated in column 'I' assume an 8 hour working day
To add extra rows, just copy and paste - the easiest way is to insert rows (Insert Menu) and copy entire rows so that you get all the formulas for the Gantt chart.
Protection is turned Off, but to protect the Gantt chart formulas from accidental typos, I recommend you turn it on (even with a blank password) under Tools, Protection, Protect Sheet.
Limitations: | In Excel 2007 or greater you can copy the formulas out horizontally to plot up to 45 years (16384 columns)
One thing the s/sheet will not attempt to do is reconcile overbooked resources - if you assign Fred to perform 10 one day tasks, all starting on the same day, it will just assume that Fred can do all the tasks at the same time.
All the dates are in Year-Month-Day format (international)